## Summary
Iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 05/11/2021 - 05/18/2021 | Project requirements, high level design, architecture, technology stack, and presentation. | Decided which technologies to be used - Python/Flask, HTML5/JS, SQLite, pycrypto. | Came up with project requirements and presentation. | Meet earlier for next iteration. | 0 | 0 | 0 | 0 | 0 | 37.6 | 29 | 1.3 | 3 | 6 | 8 | 0 | 0 | 7.5 | 5 | 1.5
1 | 05/18/2021 - 06/01/2021 | Skeleton of application implemented, with a few pages (login, signup). Application security discussions and implementation (password hashing, sessions). Database design and tables. Documentation for setting up and running the application. | Found appropriate libraries for password hashing and session management. Discussed how to approach secure encryption of the user's password vault. | Additional requirements, meetings, discussions about tasks, code walkthroughs, presentations. | n/a - continue with the current velocity. | 2 | 8 | 17 | 4 | 13 | 73.7 | 48.7 | 5.5 | 14 | 3.5 | 10 | 14 | 1.5 | 7.2 | 1.5 | 0
2 | 06/01/2021 - 06/15/2021 | Implement: * Adding, editing, and deleting items from the user’s vault. * Automatic strong password generation. * Automated testing. | Came up with algorithm for automatic generation of strong passwords for user's vault items. Figured out how to integrate our tests with GitHub Actions so that tests are run automatically when someone wants to merge their code with the main branch. | Meetings about deciding which features to implement and which tasks to assign to which team members. Code walkthroughs, presentations. | n/a - continue with the current velocity. | 8 | 8 | 9 | 5 | 4 | 82 | 59.5 | 5 | 9 | 2 | 10 | 27 | 4.5 | 7 | 0.5 | 0
3 | 06/15/2021 - 06/22/2021 | * Implement CSRF protection * Add more automated tests * Implement blueprints for app pages * Implement encryption of the user's vault * Setup/add code coverage reporting * Final project presentation. | Implement CSRF protection using a the Flask WTF library. Add automated tests for models. Implement Blueprints for splitting up the large main routing file and making it more modular. Implement vault encryption so that the user's data is not exposed in case of a database leak. Generate code coverage report, and document how to generate it in the future. | Meetings to decide which features to implement, and which tasks to assign to which team members. Prepare and present final presentation. | n/a - continue with the current velocity. | 11 | 0 | 3 | 3 | 0 | 37.5 | 27.5 | 2 | 3.5 | 0.5 | 1 | 15.5 | 5.5 | 3 | 0.5 | 1

## Project Contribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Francis Xavier Pulikotil | Management plan | Add a password entry Delete a password entry | Introduction Key Algorithms - Algorithm to encrypt the vault | Testing metrics - Code coverage report - Automated/Manual bug counts | iteration 0 iteration 2 final | Initial version of flask app Login, signup, vault items pages Unit and integration tests Vault encryption Setup/Run/Test instructions. | Unittests for model classes (user/vault/vault item) Integration test for signup page | Automated unit tests on GitHub | Scheduled/drove meetings, came up with agenda, helped other members.
Alexander Dewhirst | Proposed High level Requirements | SQLite Find out how to manage encryption and storage of user data | Design Patterns Software Architecture | N/A | iter1 final | articture unittest etc.. | item/items testing | helped | helped
Zhaowei Gu | Quality Assurance Plan - Metrics - Inspection/Review Process - Testing - Defect Management | Python unittest setup for automated/manual testing Add a confirm password box in the register screen Create password complexity requirements | Classes and Methods Design Patterns | Test Summary Tests Reports Testing Metrics | iter1 final worked on the PPT | unittest | manual test our program with user stories and scrrenshots write some unittesting in the unittest | setup my own git and slack etc. and learned from group member how to use git better as a group | helped be active
Andrew Klimentyev | Configuration management | Encrypt password for user logon | Section on passlib in Key Algorithms | n/a | helped with iter 2 presentation Final | Csrf token, Password hashing
Kayla Bayusik | "LastPass" related work blurb Functional/nonfunctional requirements contributions Security requirements | Register new user story New user tasks New user acceptance tests User account login story User login tasks User login acceptance tests | Database design section Database design diagrams/models Security design section Key algorithms section UI design section UI design wireframes | N/A | Wireframe slides Security slides Iter1 video | Encryption algorithm - but Francis did it better and cleaner... | Manual tests of my encryption - rather than using libraries I attempted to write the encryption algorithm pieces myself so there was lots of testing/ bugs for me to work out | N/A | Meeting scheduling

## Zhaowei Gu
Lead Roles: Quality Assurance leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10/2021 - 05/17/2021 | 14.3 | 13 | 1.3 | 0 - learn git and class and group struucture 1 - define high level requirements 2.- design the quality assurance plan 5 - make project plan 6 - set up git,slack,etc.. 7 - looking for project logo | 3 | 1 | 6 | 0 | 0 | 1 | 1.5 | 0.5 | 1. Write and design SPPP 2. Set up git, commit a test message on git | 1. not familiar with frameworks, hard to write any code on it 2. Previous leader did not start early and dropped the class we have a late start 3. not familiar with GitHub slack etc. | 1. Learn frameworks 2. Already learned how to use GitHub slack etc. 3. Got a new group leader and we are going to meet early and multiple time next week | 1. Learn frameworks 3. Got a new group leader and we are going to meet early and multiple time next week | 15
2 | 05/18/2021 - 05/24/2021 | 7 | 4.5 | 2.5 | 0 - learning Unit-test, Selenium 2 - QA section revision 5 - take note of team meeting | 3 | 0 | 0.5 | 0 | 0 | 1 | 0 | 0 | 1. Write and renew SPPP 2. User stories | 1. unsure how exactly to implement a unit test for the code we have | 1. Talk to develop let them write unit test for the code they wrote 2. Start studying Selenium with python to use for E2E test | 1. Talk to develop let them write unit test for the code they wrote 2. Start studying Selenium with python to use for E2E test 3. Start working on Selenium 4. Write a user perspective testing plan | 7
3 | 05/25/2021 - 05/01/2021 | 11 | 8 | 3 | 0 - Learning how to use SQLite3 and Flask app and learn unit-test with flask, and db and virtual env 2 - presentation ppt 1 - define user stories 3 - implment and setup for unit-test, sppp, sdd 5 - communicate with Francis, got help setup the unittest 5 - presentation/record | 3 |  | 0.5 | 3 | 1 | 0.5 |  |  | 1. unittest 2. SPPP 3. Presnetation | 1. automatic unittest 2. Find the tool to use to generate Classes and Methods, link application API | 1. continue to work on unittest, finish testing then fugure out how to automate testing | 1. unittest continue 2. Find the tool to use to generate Classes and Methods, link application API | 14
4 | 06/01/2021 - 06/08/2021 | 7.5 | 6 | 1.5 | 0 - Learning pyDoc to condiment project method and class 3 - test_login.py 4 - modify and revise unittests 5 - communicate with Francis, got complete and revise previous and fix new unites issue | 2 |  |  | 1 | 2 | 1 |  |  | 1. unittest | 1. pyDoc seemes working differently with flask | 1. reviewed on how to do pyDoc, but now compeltely sure how to implement the method into our project | 1. unittest continue 2. pyDoc start | 7
5 | 06/08/2021 - 06/15/2021 | 10.5 | 8 | 2.5 | 0 - Learn manual testing 2 - make SDD and tesing docx look better 3 - test.docx 4 - manual testing, unittesting | 1.5 |  | 0.5 | 1.5 | 1 |  |  |  | 1. test.docx 2. SPPP.docx 2. manual testing | none | none | 1. write more unittest 2. work on pyDoc 3. help group member | 7
6 | 06/15/2021 - 06/22/2021 | 4 | 2 | 2 | 3 - test.docx, PPT, SPPP, etc 4 - manual testing |  |  |  | 1 | 1 |  |  |  | 1. FInal presentation 2. testing.doc | none | none | none | 0

## Francis Xavier Pulikotil
Lead Roles: Team / Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/11/2021 - 05/18/2021 | 6.5 | 4.5 | 2 | 1 - define high level project requirements, 2 - high level design 5 - create meeting agenda, create/record presentation 6 - set up git 7 - research git, pivotal tracker |  | 1 | 1 |  |  | 1 | 0.5 | 1 | Discuss and decide project details, high level design, and prepare presentation. Update SPPP document. | n/a | n/a | Meet with team, discuss, and create tasks in pivotal tracker. Start working on project. | 6
2 | 05/18/2021 - 05/25/2021 | 5.7 | 3.2 | 2.5 | 3 - implemented poc python/flask application 2 - review UI design mockups 5 - schedule, moderate, record team meetings |  |  | 0.5 | 2.5 |  | 0.2 |  |  | Imlement poc Python/Flask app, discuss and review UI design mockups with the team, schedule/moderate meetings with the team, record/edit meeting recordings, upload to common location for team to review. | n/a | n/a | Merge poc of Python/Flask app, and the SQLite poc into a single application, with a few pages implemented, which will serve as the main application for everyone to start working on. | 6
3 | 05/25/2021 - 06/01/2021 | 11 | 8 | 3 | 3 - Implemented login, sign up pages of application, database tables, and session management. 4 - Developer testing. 5 - Demoed implemented features to the team. Worked with Zhaowei to set up unittest for the application. 0 - Researched session management for Flask applications. 2 - Reviewed wireframes of various pages of the application. | 1 |  | 0.5 | 5 | 0.5 | 1 |  |  | Implemented the login and signup pages of the PassMan application, including session management, database tables and theming. integrated with Andrew K's code for password hashing (resolving conflicts and relocating code). Set up meetings with the team, and led with the created agenda for the week. Was responsible for recording and uploading the meeting videos. | 1. Figuring out how Flask applications do various things like application contexts, cookies, and sessions. | 1. Resolved. | Review other members' code and provide feedback. Set up and moderate meetings with the team. Continue working on application features. | 8
4 | 06/01/2021 - 06/08/2021 | 6 | 4 | 2 | 0 - research on encryption 2 - based on professor's input, designed a detailed algorithim to encrypt/decrypt the user's vault 3 - code reviews 5 - setup/moderate/record group meetings, take meeting notes, demo current state of the project in meeting to professor and facilitator | 0.5 |  | 1.5 | 1 |  | 1 |  |  | Based on Professor's input, designed a defailed algorithm to encrypt/decrypt the user's vault in PassMan. The algorithm is documented in the SDD document as well as in the meeting minutes (6/02). Perfomed code reviews, provided feedback and additional help with unittests. Set up meetings, created agendas, took meeting notes, and contributed to discussions with the team/professor/facilitator about the project. | 1. Come up with a robust algorithm for encrypting the user's vault. | 1. Resolved. | Continue working towards the project features. Review other member's code; provide feedback. Setup and moderate meetings with the team. Make sure group deliverables are created and delivered on time. | 6
5 | 06/08/2021 - 06/15/2021 | 15.5 | 10.5 | 5 | 2 - design pages for add/edit/delete vault items; automatic password generator. 3 - implement adding, editing, and deleting items from the user’s vault; automatic strong password generation. 4 - testing of implemented features. 5 - setup/drive/record meetings with group; demos; presentation. 6 - setup automated testing. |  |  | 2 | 6 | 1 | 1 | 0.5 |  | Design/implementation of add/edit/delete vault items feature. Design/implementation of automatic strong password generation feature. Set up/drive meetings, create agendas, and record/edit meeting videos. Contribute to presentation. | None | None | Contribute to the vault encryption feature, review other member's code, provide feedback. Setup/drive meetings with the team. Make sure group deliverables are created and delivered on time. | 6
6 | 06/15/2021 - 06/22/2021 | 12.5 | 10.5 | 2 | 3 - implement vault encryption. 4 - add automated tests for models 5 - setup/drive/record meetings, presentation. 6 - setup code coverage report generation. |  |  |  | 5 | 4 | 1 | 0.5 |  | Implemented vault encryption according to the algorithm discussed in the team meeting with professor. Added more automated tests for model classes so that they do not break in the future. Setup/drive/record meetings and final presentation. | None | None | None | 0

## Andrew Klimentyev
Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/16-05/17 | 5 | 3 | 2 | 1 - define high level requirements, 6 - set up git | 0 | 2 |  |  |  | 0 | 1 |  | 1. Write SPPP configuration 6. Set up git, commit a test message on git | 1. not familar with Flask framework 2. Late start | 1. Research and learn flask 2. Revise team meeting schedule | 0 - Learn Flask 1 - Discuss and establish merge guidelines 3 - Start project | 6
2 | 05/18-05/25 | 5 | 3 | 2 | 0-Research pycrypto, and develop poc | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0. Research encryption for user passwords and entries | 1. pycrypto itself is depreciated, need to find alternatives | 1. Look into passlib | 0. Finish Encryption and start implementation | 5
3 | 05/26-06/01 | 6 | 2 | 4 | 3-Implement hashing user passwords for login | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 3 - Implemented user login password hashing in the db and verification | 3. Hash must be retrieved from database before verification instead of using a select statement to match. Hash can't be used for decryption of vault, as it is one way | 1. Look into method for using user entered password as decryption for vault information | 0. Find way to use user password as decryption for vault | 3
4 | 06/02-06/08 | 4 | 2 | 2 | 0. Research storing password decryption key in db | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 Researched methods for encrypting vault passwords | 0. Implementation blocker | 0. Modify implementation approach | 3. Add encryption | 3
5 | 06/09-/06/15 | 7 | 5 | 2 | 0. Research Csrf token 3. Implement Csrf token | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 Researched implementing csrf token in Flask, 3. Added Csrf token to fields | 3. Csrf needs to be disabled during unit tests | 0. Csrf disabled during tests | 4. Add testing for csrf | 3
6 | 06/16-06/21 | 5 | 3 | 2 | 0. Research testing for crf token 7. Prepare for presentation | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0. Refined Csrf token | None | complete | Na | 0

## Kayla Bayusik
Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10/2021 - 05/17/2021 | 6.8 | 5.5 | 1.3 | 1 - define requirements 5 - meet the team, set up WhenIsGood to find ideal meeting times 6 - Setup git, drive, slack, pivotal tracker | 0 | 1 | 0 | 0 | 0 | 2.5 | 2 | 0 | Take weekly meeting minutes Edit SPPP document |  |  | Refine requirements into scope definition Begin opening pivotal tracker issues Define user flows / use cases | 10
2 | 05/18/2021 - 05/24/2021 | 8.5 | 6 | 2.5 | 1 - user stories / tasks for the lab 2 - designed UI mockups 5 - further WhenIsGood work for changing schedules | 0 | 1.5 | 4 | 0 | 0 | 0.5 | 0 | 0 | UI mockups User stories | Certain undecided mockup aspects | Issue resolved - discussed with team | Finish / record iteration 1 presentation video Finalize security requirements Fill in SDD sections Some undecided implementation work | 10
3 | 05/26/2021 - 06/01/2021 | 7.5 | 6 | 1.5 | 0 - learning to properly run Francis's flask app 1 - further refine user stories, outline security requirements 2 - created database design diagrams 5 - Finish and record iteration 1 presentation | 1 | 1.5 | 2 | 0 | 0 | 1.5 | 0 | 0 | Database diagrams Iteration 1 presentation |  |  | Implement cryptography Edit CSS to match mockups | 2021-06-08
4 | 06/01/2021 - 06/08/2021 | 6.5 | 5 | 1.5 | 2 - begin translating my UI mockups into actual CSS designs 3 - begin implementing the encryption algorithm detailed by the professor in our most recent meeting | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | (Not quite complete) Encryption |  |  | Finish encryption algorithm Finish website CSS | 2021-06-08
5 | 06/09/2021 - 06/15/021 | 14 | 12 | 2 | 1 - clarifying and expanding the algorithm requirements in the SDD doc 3 - developing the security algorithm | 0 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | SDD section Encryption Implementation
6 | 06/16/2021 - 06/22/2021 | 8 | 6 | 2 | 3 - Finishing the security algorithm, despite us ultimately using Francis's version | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | Encryption Implementation | Encryption bugs |  | N/A | N/A

## AlexanderDewhirst
Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05.11.21-05.18.21 | 5 | 3 | 2 | 1 - Discuss project requirements 2 - Discuss design and implementation 5 - Meeting. Presentation. Setup agenda | 0 | 1 | 1 | 0 | 0 | 3 | 0 | 0 | Contribute to team proposal after discussing team project, design, and implementation. Present project. | n/a | n/a | Setup meetings with team. Delegate tasks to teammates using Pivotal Tracker. Begin project and have development workspace for each teammate. | 8
2 | 05.18.21-05.25.21 | 7 | 5 | 2 | 0 - Learning how SQLite3 is setup in a Flask app 0 - Setup Python virtual environment to manage environment variables 1 - Determine requirement of virtual environment 2 - Initialize application with database and tables created on __init__ 3 - Create POC for Flask with SQLite3 5 - Write up requirements for UI Mockups 6 - Configure environment variables with Python virtualenv | 3 | 0.5 | 2 | 0.5 | 0 | 0.5 | 0.5 | 0 | Determine how we will integrate with SQLite3 | n/a | n/a |  | 7
3 | 05.25.21-06.02.21 | 5 | 3 | 2 | 3 - Complete SQLite3 POC 5 - Two meetings with team to discuss project iteration 5 - Work on Architecture section of SDD document. | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | Complete POC ticket | n/a | n/a |  | 5
4 | 06.02.21-06.09.21 | 6 | 4 | 2 | 2 - Refactor models to directory 2 - Refactor to use partial views 2 - Add feature to seed the database 2 - Add Vault model, database table, and change model relationships 2 - Remove cross-model dependency to separate concerns 2 - Create Helper directory and class 3 - Review code | 0 | 0 | 3 | 0.5 | 0.5 | 2 | 0 | 0 | Complete Architecture ticket | n/a | n/a |  | 6
5 | 06.09.21-06.16.21 | 5 | 3 | 2 | 0 - Learn about Encryption 3 - Review code | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | Learn about encryption | n/a | n/a |  | 5
6 | 06.16.21-06.23.21 | 8 | 6 | 2 | 0 - Learn different folder structures that are best suited for Blueprints 1 - Review Design leader requirements for our project 2 - Use a folder structure that allows for nested Blueprints used with a RESTful approach 3 - Create Blueprints for Sessions, Registrations, Vaults, and Vault Items 3 - Determine how to support url_for helpers with Blueprints 4 - Refactor tests for authentication to use new endpoints 5 - Meet with team, present our project | 1.5 | 0.5 | 1 | 3.5 | 0.5 | 2 | 0 | 0 | Create scalable approach to handling resources and serving routes in a RESTful manner | n/a | n/a |  | 8